## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Study LLM evaluation techniques, hallucination detection methods, RAG architecture, and existing evaluation frameworks (RAGAS, TruLens) | Must Have | None | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-02 | Design system architecture, agent responsibilities, scoring dimensions, orchestration flow, and data models | Must Have | US-01 | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-03 | Develop Evaluation Input Module - single submission interface accepting question, AI response, and reference answer | Must Have | US-02 | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-04 | Build Reference Knowledge Base - seed with SQuAD (and Wikipedia), implement chunking, embedding, and vector store indexing in ChromaDB | Must Have | US-02 | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-05 | Build Retrieval Agent to fetch top-k relevant context chunks for a given question from ChromaDB | Must Have | US-04 | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-06 | Build prototype Evaluation Agent using RAGAS semantic similarity for relevance, accuracy, completeness, and faithfulness scoring | Must Have | US-05 | Ghayathri Devi G M | Done
Sprint 1 | Sprint 1 | US-07 | Build frontend dashboard (HTML/CSS/JS) to submit evaluations and display scores | Should Have | US-03 | Ghayathri Devi G M | Done
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 19.5 | 0 | 0 | 0 | 2 | 6 | 0 | 3 | 2 | 4 | 0 | 0 | 2.5 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Research LLM evaluation techniques and RAG architecture | 2026-06-30 | 2026-06-30 | Ghayathri | Research | Done | 3 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Review RAGAS and TruLens documentation | 2026-06-30 | 2026-07-01 | Ghayathri | Research | Done | 3 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-03 | Design high-level architecture and orchestration flow diagram | 2026-07-01 | 2026-07-01 | Ghayathri | Design | Done | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-04 | Define agent responsibilities, scoring dimensions, and data models | 2026-07-01 | 2026-07-02 | Ghayathri | Design | Done | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-05 | Build FastAPI /evaluate endpoint with input validation | 2026-07-02 | 2026-07-02 | Ghayathri | Development | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-06 | Load SQuAD dataset and generate embeddings with Sentence-Transformers | 2026-07-03 | 2026-07-03 | Ghayathri | Development | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-07 | Index embeddings into ChromaDB persistent vector store | 2026-07-03 | 2026-07-04 | Ghayathri | Development | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-08 | Build retrieval_agent.py to query ChromaDB by question embedding | 2026-07-04 | 2026-07-04 | Ghayathri | Development | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-09 | Integrate RAGAS SemanticSimilarity metric for relevance/accuracy/completeness | 2026-07-05 | 2026-07-06 | Ghayathri | Development | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
US-06 | T-10 | Integrate Groq LLM-as-judge call for faithfulness / hallucination risk | 2026-07-06 | 2026-07-07 | Ghayathri | Development | Done | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
US-07 | T-11 | Build HTML/CSS/JS dashboard and wire to /evaluate API | 2026-07-07 | 2026-07-08 | Ghayathri | Development | Done | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0
US-03 | T-12 | Enable CORS middleware for frontend-backend communication | 2026-07-08 | 2026-07-08 | Ghayathri | Bug Fix | Done | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
US-06 | T-13 | End-to-end testing of input, retrieval, and evaluation pipeline | 2026-07-09 | 2026-07-09 | Ghayathri | Testing | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 (30 Jun) | None | N/A
Sprint 1 | Day 2 (1 Jul) | None | N/A
Sprint 1 | Day 3 (2 Jul) | None | N/A
Sprint 1 | Day 4 (3 Jul) | HuggingFace dataset 'squad' failed to resolve (HfUriError) | Switched to namespaced dataset name 'rajpurkar/squad'
Sprint 1 | Day 5 (4 Jul) | None | N/A
Sprint 1 | Day 6 (5 Jul) | RAGAS defaulted to OpenAI embeddings, missing API key error | Passed local Sentence-Transformers embeddings explicitly into evaluate()
Sprint 1 | Day 7 (6 Jul) | Gemini/Groq API calls timing out and hitting rate limits (429) during RAGAS evaluation | Reduced to a single LLM call for faithfulness; used RAGAS SemanticSimilarity (local) for remaining metrics
Sprint 1 | Day 8 (7 Jul) | Browser blocked frontend requests to backend (CORS) | Added CORSMiddleware to FastAPI app
Sprint 1 | Day 9 (8 Jul) | None | N/A
Sprint 1 | Day 10 (9 Jul) | None | N/A

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-06-30 | 2026-07-09 | Ghayathri Devi G M | Testing agent logic with mock/dummy data before calling real APIs | Repeatedly calling live llm APIs | Building end-to-end (input -> retrieval -> evaluation) before adding complexity | Add a mock evaluation function for local testing in Milestone 2 to avoid burning API quota
2
3
4
5
6
7