## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ghayathri Devi G M | 2026-07-03 | HuggingFace dataset load_dataset('squad') failed with HfUriError due to short-form dataset name no longer resolving | Sprint 1 | Ghayathri Devi G M | Others | Switched to namespaced dataset identifier 'rajpurkar/squad' | 2026-07-03 | Closed | Caused by HF Hub API changes, not application logic
2 | Ghayathri Devi G M | 2026-07-05 | RAGAS evaluate() defaulted to OpenAI embeddings internally, raising 'Missing credentials' OpenAIError even though Gemini/Groq was configured as the LLM | Sprint 1 | Ghayathri Devi G M | Logical | Explicitly passed local Sentence-Transformers embeddings (wrapped via LangchainEmbeddingsWrapper) into evaluate() | 2026-07-05 | Closed | RAGAS metrics need embeddings passed separately from the judge LLM
3 | Ghayathri Devi G M | 2026-07-06 | All 4 RAGAS metric jobs raised TimeoutError when calling Gemini API, likely due to default RAGAS timeout/parallel worker settings hitting free-tier rate limits | Sprint 1 | Ghayathri Devi G M | Logical | Added RunConfig(timeout=120-180, max_workers=1, max_retries=2) to slow and serialize calls | 2026-07-06 | Closed | Reduced job concurrency to fit free-tier rate limits
4 | Ghayathri Devi G M | 2026-07-06 | Gemini API returned 'Resource Exhausted' (daily quota) after repeated test runs during debugging | Sprint 1 | Ghayathri Devi G M | Others | Reduced LLM usage to a single call (faithfulness only); all other metrics moved to local RAGAS SemanticSimilarity | 2026-07-07 | Closed | Free-tier daily/per-minute quota exhausted from repeated live testing while debugging
5 | Ghayathri Devi G M | 2026-07-07 | Groq API returned 429 rate-limit error despite only 18% of daily token quota consumed | Sprint 1 | Ghayathri Devi G M | Logical | Identified as a per-minute token burst limit, not daily quota; confirmed correct lightweight model (llama-3.1-8b-instant) was configured | 2026-07-07 | Closed | Distinguish burst/TPM limits from daily/RPD limits when diagnosing 429 errors
6 | Ghayathri Devi G M | 2026-07-08 | Browser blocked frontend (index.html) requests to FastAPI backend with a CORS policy error | Sprint 1 | Ghayathri Devi G M | Standards | Added CORSMiddleware to FastAPI app allowing cross-origin requests from the frontend | 2026-07-08 | Closed | Required since frontend and backend run on different local origins
7 | Ghayathri Devi G M | 2026-07-08 | Swagger UI (/docs) showed 'No parameters' for /evaluate endpoint because raw Request object was used instead of a typed body | Sprint 1 | Ghayathri Devi G M | User Interface | Switched to Body(...) / Pydantic model so FastAPI generates a proper request body form in Swagger | 2026-07-08 | Closed | Improves auto-generated API docs and testability

## Sheet2
Logical
User Interface
Maintainability
Standards
Others